## Slide 1: ATHENS INSURANCE PARTNERS
Ameya Jamgade
Ilia Prokashev

## Slide 2: PROJECT CHARTER- ALIENSOFT IMPLEMENTATION
AGENDA
Project Description
Vision of Success
Customer requirements and goals
Sponsorship
Stakeholder
Team member
Scope
Milestones, Schedules and Deliverables
Risks

## Slide 3: PROJECT DESCRIPTION
Installation of 'Aliensoft’ software, a cloud based policy and document management software, in the underwriting department of Athens Insurance Partners company to increase work efficiency and information flow.

## Slide 4: PROJECT VISION OF SUCCESS
Improved efficiency of underwriting department
Consolidated repository of policy documents

## Slide 5: PROJECT CUSTOMER REQUIREMENTS & GOALS
CUSTOMER REQUIREMENTS
Software customized according to company’s needs
Install the Aliensoft software application on the end user workstations.
Adequate staff training
Aliensoft team adhering to predetermined timelines
GOALS
Successful implementation
Sufficiently trained end users
Acceptance of new software by users
Improved work efficiency of underwriting department

## Slide 6: PROJECT SPONSOR
Tom DiCaprio, President of Athens Insurance Partners

## Slide 7: PROJECT STAKEHOLDERS
Athens Insurance Partners
Senior Leadership
Credit underwriting team- End users
IT representative
Finance department
Project Managers
Department SME
Aliensoft Professional Services
Project Lead
Consultants
Senior Leadership
Technical Consultant
IT team
Trainer

## Slide 8: PROJECT TEAM MEMBERS
Project Manager
Project Lead
IT representative
Department SME
End user representative
Aliensoft Consultant
Aliensoft Technical Consultant
Aliensoft professionals and Trainers

## Slide 9: PROPOSED RESOURCES FROM OTHER DEPARTMENTS
IT Department: John Hawthorn
Underwriting Department: Nicholas Gilman
Finance Department: Thomas Scott
Notes: John Hawthorn has exposure to newest technologies. His enthusiasm will help the solve setbacks through innovative ideas and the IT implementation will be efficient. IT job role needs very little emphasis on politics, so his lack of political skills wouldn’t create any hindrance. Also, he is known to work long hours, so he will prove to be a very valuable resource.
Nicholas Gilman has knowledge of executing underwriting process, has excellent team management skills. His peace corps experience will help in managing stressful situations and conflicts. Even though he might get pulled away by his manager, we feel that there is enough room for him to work on both projects.
Thomas Scott is knowledgeable about the politics and inner workings and has good relationship with Tom DiCaprio. So he can play an active role as project champion and advocate for this project in case the senior management are evaluating the project’s feasibility midway. Also, Elias does not have prior experience in the insurance industry and might be looking for outside opportunities.

## Slide 10
Responsibility | Casey Avenue PM | John Hawthorn IT | Nicholas Gilman UD | Thomas Scott FD
Negotiates prices and terms with vendors |  |  |  | 
Technical requirement analysis |  |  |  | 
Technical installations |  |  |  | 
Pilot prep |  |  |  | 
Updated configuration |  |  |  | 
Training Week |  |  |  | 
Go live Week |  |  |  | 
Can support a task
Notification
Responsible
Approval

## Slide 11: PROJECT SCOPE
IN SCOPE
Customized software configuration
On-site technical consultation
Arrangement of Conference Room Pilot (CRP) to demonstrate current project status
System to system conversion of the policy system into the Aliensoft system
On-site training for end users
Go Live support
Workbook with generic functionality
Creation of custom training materials
OUT OF SCOPE
Integration with Microsoft Outlook
Back-scanning of paper files

## Slide 12: PROJECT MILESTONES, SCHEDULE & DELIVERABLES
Week | Topic
Week 1 | Kickoff Meeting
Week 2 | Initial Configuration
Week 3 | Initial Configuration
Week 4 | Technical Installs
Week 5 | Initial Configuration
Week 6 | Test Conversion
Week 7 | Conference Room Pilot Prep
Week 8 | Conference Room Pilot (CRP)
Week 9 | Updated configuration, prep for Training week
Week 10 | Training Week
Week 10 (Weekend) | Production Conversion
Week 11 | Go Live week

## Slide 13: PROJECT RISKS
Financial uncertainty
Change in insurance regulations
Cyber security
Compatibility between existing and new software
Lack of end user support
Lack of internal IT support after Go Live
Loss of interest midway from senior management
Release of advanced software in near future
Exponential increase in project costs
Senior Leadership not convinced about giving resources for this project

## Slide 14: THANK YOU!