## Sheet1
|  | Week | Cumulative Budget - No Contingency | Cumulative Budget - With Contingency | Actual Cumulative Expenses | Cost Variance (EV-AC) - No Contingency
1 | Kickoff Meeting | 1 | 8600 | 9708.3333 | 14700 | -6100
2 | Initial Configuration | 2 | 15400 | 17616.6667 | 19900 | -4500
3 | Initial Configuration | 3 | 22200 | 25525 | 27900 | -5700
4 | Technical Installs | 4 | 35700 | 40133.3333 | 47300 | -11600
5 | Initial Configuration | 5 | 42600 | 48141.6667 | 50300 | -7700
6 | Test Conversion | 6 | 50100 | 56750 | 55500 | -5400
7 | Conference Room Pilot Prep | 7 | 56075 | 63833.3333 | 61900 | -5825
8 | Conference Room Pilot (CRP) | 8 | 65575 | 74441.6667 | 81900 | -16325
9 | Updated configuration, prep for Training week | 9 | 71575 | 81550 | 87400 | -15825
10 | Training Week | 10 | 88025 | 99108.3333 | 98500 | -10475
| Production Conversion | 0 | 102025 | 114216.6667 | 108700 | -6675
11 | Go Live week | 11 | 113625 | 126925 | 121250 | -7625
Aliensoft Implementation - Budget (Planned Value)
|  | Aliensoft Project Mgmt Hrs | Aliensoft Project Mgmt Cost/Hr | Aliensoft Project Mgmt Cost | Aliensoft Consulting Hrs | Aliensoft Consulting Cost/Hr | Aliensoft Consulting Cost | Aliensoft Travel Expenses | Aliensoft Notes | AIP Project Mgmt Hrs | AIP Project MGMT Cost/HR | AIP Project Mgmt Cost | AIP Resource Hrs | AIP Resource Cost / Hour | AIP Resource Cost | AIP Non-Recurring Cost | Total Per Week no Contingency | Cumulative Total per week no Contingency | Contingency | Total per week with Contingency | Cumulative Total per Week With Contingency | AIP notes
1 | Kickoff Meeting | 14 | 200 | 2800 | 10 | 200 | 2000 | 1500 | Project lead | 14 | 50 | 700 | 8 | 75 | 600 | 1000 | 8600 | 8600 | 1108.3333 | 9708.3333 | 9708.3333 | PM and SME
2 | Initial Configuration | 0 | 200 | 0 | 30 | 200 | 6000 |  | Consultant - offsite | 4 | 50 | 200 | 8 | 75 | 600 |  | 6800 | 15400 | 1108.3333 | 7908.3333 | 17616.6667 | NG, PM
3 | Initial Configuration | 0 | 200 | 0 | 30 | 200 | 6000 |  | Consultant - offsite | 4 | 50 | 200 | 8 | 75 | 600 |  | 6800 | 22200 | 1108.3333 | 7908.3333 | 25525 | NG, PM
4 | Technical Installs | 0 | 200 | 0 | 28 | 200 | 5600 | 2000 | Technical Consultant - onsite | 4 | 50 | 200 | 36 | 75 | 2700 | 3000 | 13500 | 35700 | 1108.3333 | 14608.3333 | 40133.3333 | PM & IT Representative
5 | Initial Configuration | 2 | 200 | 400 | 28 | 200 | 5600 |  | Consultant - offiste | 6 | 50 | 300 | 8 | 75 | 600 |  | 6900 | 42600 | 1108.3333 | 8008.3333 | 48141.6667 | NG, PM
6 | Test Conversion | 0 | 200 | 0 | 22 | 200 | 4400 |  | Conversion cosultant- offsite | 8 | 50 | 400 | 36 | 75 | 2700 |  | 7500 | 50100 | 1108.3333 | 8608.3333 | 56750 | IT Representative, Department SME
7 | Conference Room Pilot Prep | 3 | 200 | 600 | 16 | 200 | 3200 |  | Consultant - offsite | 6 | 50 | 300 | 25 | 75 | 1875 |  | 5975 | 56075 | 1108.3333 | 7083.3333 | 63833.3333 | IT Representative and NG
8 | Conference Room Pilot (CRP) | 3 | 200 | 600 | 22 | 200 | 4400 | 1500 | Consaltant- onsite | 6 | 50 | 300 | 36 | 75 | 2700 |  | 9500 | 65575 | 1108.3333 | 10608.3333 | 74441.6667 | Project Manager, IT Representative, Department SMEs
9 | Updated configuration, prep for Training week | 3 | 200 | 600 | 22 | 200 | 4400 |  | Consultant - offsite | 8 | 50 | 400 | 8 | 75 | 600 |  | 6000 | 71575 | 1108.3333 | 7108.3333 | 81550 | IT Representative
10 | Training Week | 3 | 200 | 600 | 36 | 150 | 5400 | 2000 | Trainer - onsite for full week | 5 | 50 | 250 | 36 | 75 | 2700 | 5500 | 16450 | 88025 | 1108.3333 | 17558.3333 | 99108.3333 | Project Manager, IT Representative, Department SMEs, End Users
| Production Conversion | 0 | 200 | 0 | 14 | 200 | 2800 |  | Conversion Consultant - Weenend work - offsite | 0 | 50 | 0 | 16 | 75 | 1200 | 10000 | 14000 | 102025 | 1108.3333 | 15108.3333 | 114216.6667 | IT Representative, weekend work
11 | Go Live week | 4 | 200 | 800 | 36 | 150 | 5400 | 2000 | Trainer - onsite for full week | 8 | 50 | 400 | 40 | 75 | 3000 |  | 11600 | 113625 | 1108.3333 | 12708.3333 | 126925 | Project Manager, IT Representative, Department SMEs, End Usersend users
| Total Dollars |  |  | 6400 |  |  | 55200 | 9000 |  |  |  | 3650 |  |  | 19875 | 19500 | 113625 |  | 13300 | 126925
| Total Units | 32 | hours |  | 294 | hours |  |  |  | 73 | hours |  | 265 | hours |  |  |  |  | 11.71%
Aliensoft Implementation - Actual Costs
Week |  | Aliensoft Project Mgmt Hrs | Aliensoft Project Mgmt Cost/Hr | Aliensoft Project Mgmt Cost | Aliensoft Consulting Hrs | Aliensoft Consulting Cost/Hr | Aliensoft Consulting Cost | Aliensoft Travel Expenses | Aliensoft Notes | AIP Project Mgmt Hrs | AIP Project MGMT Cost/HR | AIP Project Mgmt Cost | AIP Resource Hrs | AIP Resource Cost / Hour | AIP Resource Cost | AIP Non-Recurring Cost | Actual Per Week | Cumulative Actual Per Week | AIP Notes
1 | Kickoff Meeting | 8 | 200 | 1600 | 24 | 200 | 4800 | 2500 | 2 Aliensoft consultants. | 24 | 50 | 1200 | 48 | 75 | 3600 | 1000 | 14700 | 14700 | AIP: Casey, IT and UW MS Project software
2 | Initial Configuration | 2 | 200 | 400 | 20 | 200 | 4000 |  |  | 4 | 50 | 200 | 8 | 75 | 600 |  | 5200 | 19900
3 | Initial Configuration | 2 | 200 | 400 | 20 | 200 | 4000 |  |  | 4 | 50 | 200 | 8 | 75 | 600 | 2800 | 8000 | 27900 | GA Tech Team event
4 | Technical Installs | 4 | 200 | 800 | 50 | 200 | 10000 | 1300 | Hardware Install | 8 | 50 | 400 | 52 | 75 | 3900 | 3000 | 19400 | 47300 | Part Time IT Consultants, Event2-IT
5 | Initial Configuration | 0 | 200 | 0 | 10 | 200 | 2000 |  | Add. Configuration | 2 | 50 | 100 | 12 | 75 | 900 |  | 3000 | 50300
6 | Test Conversion | 2 | 200 | 400 | 20 | 200 | 4000 |  | Test conversion | 4 | 50 | 200 | 8 | 75 | 600 |  | 5200 | 55500 | Test conversion
7 | Conference Room Pilot Prep | 2 | 200 | 400 | 20 | 200 | 4000 |  |  | 4 | 50 | 200 | 24 | 75 | 1800 |  | 6400 | 61900 | More preparation than expected
8 | Conference Room Pilot (CRP) | 8 | 200 | 1600 | 60 | 200 | 12000 | 3400 |  | 24 | 50 | 1200 | 24 | 75 | 1800 |  | 20000 | 81900 | 3 people attended CRP
9 | Updated configuration, prep for Training week | 2 | 200 | 400 | 20 | 200 | 4000 |  |  | 4 | 50 | 200 | 12 | 75 | 900 |  | 5500 | 87400
10 | Training Week | 2 | 200 | 400 | 40 | 150 | 6000 | 1500 | Training room etc. | 4 | 50 | 200 | 40 | 75 | 3000 |  | 11100 | 98500 | UW attends training
| Production Conversion | 0 | 200 | 0 | 16 | 200 | 3200 |  | IT conversion cheaper than expected | 0 | 50 | 0 | 0 | 75 | 0 | 7000 | 10200 | 108700
11 | Go Live week | 2 | 200 | 400 | 40 | 150 | 6000 | 1650 |  | 4 | 50 | 200 | 40 | 75 | 3000 | 1300 | 12550 | 121250
| Total Dollars |  |  | 6800 |  |  | 64000 | 10350 |  |  |  | 4300 |  |  | 20700 | 15100 | 121250
| Total Units | 34 | hours |  | 340 | hours |  |  |  | 86 | hours |  | 276 | hours

## Sheet2
Resource Level
Alientsoft Project Mgnt |  |  | 40 | hrs | 11 | weeks | 3.6364 | hours peer week
Aliensoft Consultants |  |  | 25.4545 | hrs | 11 | weeks | 20 | hours pwer week
AIP Project MGMT |  |  | 88 | hrs | 11 | weeks | 8
Appendix 1 – Aliensoft Professional Services Pricing
SKU | Description | Quantity | Unit of Measure (UOM) | Unit Price | Total
1238 | Project Management | 40 | HRS | 200 | 8000 | 8000 | 0
1239 | Consulting Services | 80 | HRS | 200 | 16000 | 16000 | 0
1240 | Technical Consulting Services | 60 | HRS | 200 | 12000 | 12000 | 0
1241 | Conversion Consulting Services | 60 | HRS | 200 | 12000 | 12000 | 0
1242 | Training Services | 40 | HRS | 150 | 6000 | 6000 | 0
1243 | Go Live Services | 40 | HRS | 150 | 6000 | 6000 | 0
60000
320
| deduct pm | 40
280